## Main
| Today | Copy this doc and follow the link below for instructions. |  |  | 93.5 | 0 | 106 |  |  | 47 | 2 | 3 | 4 | 3 | 4 | 3 | 4 | 3 | 4 | 3 | 4 | 3 | 4 | 3
| 2016-12-16 | http://bazald.com/eecs-494/burndown |  |  | Hours | Hours | Hours |  |  | Wed | Fri | Mon | Fri | Mon | Fri | Mon | Fri | Mon | Fri | Mon | Fri | Mon | Fri | Mon | Bug Statuses are used below in the bug area | Bug
# | Rank | Task | Assn | Assist | Est. | Rem. | Worked |  |  | 2016-10-26 | 2016-10-28 | 2016-10-31 | 2016-11-04 | 2016-11-07 | 2016-11-11 | 2016-11-14 | 2016-11-18 | 2016-11-21 | 2016-11-25 | 2016-11-28 | 2016-12-02 | 2016-12-05 | 2016-12-09 | 2016-12-12 | Detailed Information | Status
Task Assignments | [25 empty] | Reported
5 | 1 | Brainstorming | ALL |  | 2 | 0 | 2 |  | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Assigned
6 | 1 | Settle on Idea | ALL |  | 1 | 0 | 1 |  | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Active
7 | [25 empty] | Verify?
Level
8 | 1 | Ship Exterior | SS |  | 6 | 0 | 14 |  | 6 | 6 | 6 | 6 | 6 | 6 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Fixed
9 | 1 | Ship Interior | SS |  | 4 | 0 | 7 |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Deferred
| 1 | Space Layout | YP |  | 4 | 0 | 4 |  | 4 | 4 | 4 | 4 | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1 | Endgame | YP |  | 2.5 | 0 | 0.5 |  | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 2 | 2 | 2 | 0
| 1 | Map | SS |  | 2 | 0 | 2 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0
10 |  | Asteroids | [23 empty] | Fact of Life
| 1 | Model | YP |  | 2 | 0 | 2 |  | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1 | Health Status | YP |  | 2 | 0 | 2 |  | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1 | Movement | YP | SS | 2 | 0 | 2 |  | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Players
| 1 | Readycheck Role Choice | SS |  | 2 | 0 | 2 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0
11 | 1 | Ship Movement | YP | SS | 4 | 0 | 1 |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Can't Repro
12 | 1 | Ship Camera | YP |  | 2 | 0 | 2 |  | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | 1 | Player Movement | AL |  | 4 | 0 | 1 |  | 4 | 4 | 4 | 4 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0
14 | 1 | Player Camera | AL |  | 2 | 0 | 1 |  | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
15
17 |  | Engineer Interactions
18 | 1 | Fix hull breaches | AL | SS | 2 | 0 | 2 |  | 2 | 2 | 2 | 2 | 2 | 2 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
19 | 1 | Puzzle to fix engine | AL |  | 3 | 0 | 3 |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0
20 | 1 | Turret | AL |  | 3 | 0 | 1.5 |  | 3 | 3 | 3 | 3 | 3 | 3 | 1.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0
21 | 1 | Puzzle to fix gravity generator | AL |  | 1 | 0 | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 0.5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
23 | 1 | Interaction Indicators | YP |  | 0.5 | 0 | 0.5 |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0
22 |  | Pilot Interactions
23 | 1 | Fire primary weapon | YP |  | 1 | 0 | 1 |  | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
24 | 2 | Indicators for enemy ship | SS |  | 1 | 0 | 2 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0
26 | 1 | Shields | SS |  | 2 | 0 | 2 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0
26 | 1 | Boosts | SS |  | 2 | 0 | 1 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0
26 | 1 | Power Bar | AL |  | 2 | 0 | 2 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0
27 |  | Ship Effects
28 | 2 | Gravity loss | SS | AL | 2 | 0 | 2 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
30
31 |  | Sounds | CP |  | 1 | 0 | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
32 | 2 | Shooting | CP |  | 1 | 0 | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
| 2 | Low Health Alert | CP |  | 1 | 0 | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
| 2 | Background Music | YP |  | 1 | 0 | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
33 | 3 | Miscellaneous Engineer Interaction Sounds | CP |  | 1 | 0 | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0
34 |  | Menus
35 | 1 | Start Menu | YP |  | 1 | 0 | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
37 | 1 | Game Over | YP |  | 1 | 0 | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0
38 | 1 | Tutorial | YP |  | 2 | 0 | 1 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 1 | 0 | 0 | 0
39 |  | Animations
40 | 3 | Engineer Animations | CP | AL | 3 | 0 | 3 |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 2.5 | 2.5 | 2.5 | 2.5 | 2.5 | 0
42 |  | Engineer Wrench | CP |  | 2 | 0 | 2 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0
43 | 1 | InControl | CP |  | 4 | 0 | 3 |  | 4 | 4 | 4 | 4 | 4 | 4 | 3 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
44 | 2 | Damage distribution | CP |  | 2 | 0 | 2 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0
45
46 |  | Textures
48 | 2 | Interior Textures | SS |  | 3 | 0 | 3 |  | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0
49
50 | 1 | Balancing | ALL |  | 10 | 0 | 4 |  | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 10 | 4 | 1 | 1 | 0 | 0 | 0
51 |  | Polish | ALL |  | 8 | 0 | 8 |  | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 5 | 5 | 0
52
53 | 3 | bullet explosions | AL |  | 0.5 | 0 | 0.5 |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0
54 | 3 | Gameover cutscene | AL |  | 1 | 0 | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
55 | 3 | Fade Screen Transitions | AL |  | 1 | 0 | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
56 |  | Engineer Tutorial | CP |  | 1 | 0 | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0
57 |  | Wrench Sound Effect | AL |  | 0.5 | 0 |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0
58
59
60
61
62
63
64
65
66
67
68
69
70
71
72
73
74
75
76
77
78
79
80
81
82
83
84
85
86
87
88
89
90
91
92
93
94
95
96
97
98
99
100
101
102
103
104
105
Bugs to be Fixed!!! | [24 empty] | Fix Description (if unusual or useful to later generations) | Status
107 |  | Stop ships from being able to go through each other | SS |  | 1 | 0 | 1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | Fixed
110 |  | Clamp turret's y-axis | AL |  | 0.5 | 0 | 0.5 |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 |  | Reported
111 |  | Adjust ship damage levels | CP |  | 0.5 | 0 | 0.5 |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 |  | Reported
112 |  | Destroy bullet after certain amount of time | YP |  | 0.5 | 0 | 0.5 |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 |  | Reported
113 |  | Stop camera from clipping through walls | SS |  | 0.5 | 0 | 0.5 |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 | 0 | 0 |  | Fixed
114 |  | Delay winning scene | AL |  | 0.5 | 0 | 0.5 |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 |  | Reported
115 |  | Make boost more obvious | YP |  | 0.5 | 0 | 0.5 |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 |  | Reported
116 |  | Vibrate when ships hit | CP |  | 0.5 | 0 | 0.5 |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  | Reported
117 |  | Ships dont start at same time | AL |  | 0.5 | 0 | 0.5 |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 |  | Reported
118 |  | turret bullet bug | AL |  | 0.5 | 0 | 0.5 |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 |  | Reported
119 |  | hull breach refactor ui | AL |  | 0.5 | 0 | 0.5 |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 |  | Reported
120 |  | Gameover scene replay button delay | AL |  | 0.5 | 0 | 0.5 |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 |  | Reported
121 |  | Engine always breaks first | CP |  | 0.5 | 0 | 0.5 |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  | Reported
122 |  | Countdown after respawn | AL |  | 0.5 | 0 | 0.5 |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  | Reported
123 |  | Ship random damage | CP |  | 0.5 | 0 | 0.5 |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | 0 |  | Reported
124 |  | Reset button in game for showcase | AL |  | 0.5 | 0 |  |  | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0 |  | Reported
125 | [25 empty] | Reported
126 | [25 empty] | Reported
127 | [25 empty] | Reported
128 | [25 empty] | Reported
129 | [25 empty] | Reported
130 | [25 empty] | Reported
131 | [25 empty] | Reported
132 | [25 empty] | Reported
133 | [25 empty] | Reported
134 | [25 empty] | Reported
135 | [25 empty] | Reported
136 | [25 empty] | Reported
137 | [25 empty] | Reported
138 | [25 empty] | Reported
139 | [25 empty] | Reported
140 | [25 empty] | Reported
141 | [25 empty] | Reported
142 | [25 empty] | Reported
143 | [25 empty] | Reported
144 | [25 empty] | Reported
145 | [25 empty] | Reported
146 | [25 empty] | Reported
147 | [25 empty] | Reported
148 | [25 empty] | Reported
149 | [25 empty] | Reported
150 | [25 empty] | Reported
151 | [25 empty] | Reported
152 | [25 empty] | Reported
153 | [25 empty] | Reported
154 | [25 empty] | Reported
155 | [25 empty] | Reported
156 | [25 empty] | Reported
157 | [25 empty] | Reported
158 | [25 empty] | Reported
159 | [25 empty] | Reported
160 | [25 empty] | Reported
161 | [25 empty] | Reported
162 | [25 empty] | Reported
163 | [25 empty] | Reported
164 | [25 empty] | Reported
165 | [25 empty] | Reported
166 | [25 empty] | Reported
167 | [25 empty] | Reported
168 | [25 empty] | Reported
169 | [25 empty] | Reported
170 | [25 empty] | Reported
171 | [25 empty] | Reported
172 | [25 empty] | Reported
173 | [25 empty] | Reported
174 | [25 empty] | Reported
175 | [25 empty] | Reported
176 | [25 empty] | Reported
177 | [25 empty] | Reported
178 | [25 empty] | Reported
179 | [25 empty] | Reported
180 | [25 empty] | Reported
181 | [25 empty] | Reported
182 | [25 empty] | Reported
183 | [25 empty] | Reported
184 | [25 empty] | Reported
185 | [25 empty] | Reported
186 | [25 empty] | Reported
187 | [25 empty] | Reported
188 | [25 empty] | Reported
189 | [25 empty] | Reported
190 | [25 empty] | Reported
191 | [25 empty] | Reported
192 | [25 empty] | Reported
193 | [25 empty] | Reported
194 | [25 empty] | Reported
195 | [25 empty] | Reported
196 | [25 empty] | Reported
197 | [25 empty] | Reported
198 | [25 empty] | Reported
199 | [25 empty] | Reported
200 | [25 empty] | Reported
201 | [25 empty] | Reported
202 | [25 empty] | Reported
203 | [25 empty] | Reported
204 | [25 empty] | Reported
205 | [25 empty] | Reported
206 | [25 empty] | Reported
207
208
Interpreted Data
210 |  | Days | [6 empty] | 47 | 47 | 45 | 42 | 38 | 35 | 31 | 28 | 24 | 21 | 17 | 14 | 10 | 7 | 3 | 0
211 |  | Optimum | [5 empty] | Line | 93.5 | 93.5 | 89.5213 | 83.5532 | 75.5957 | 69.6277 | 61.6702 | 55.7021 | 47.7447 | 41.7766 | 33.8191 | 27.8511 | 19.8936 | 13.9255 | 5.9681 | 0
212
213 |  | Sum | [6 empty] | 94.5 | 94.5 | 94.5 | 94.5 | 94.5 | 94.5 | 94.5 | 94.5 | 94.5 | 94.5 | 94.5 | 94.5 | 94.5 | 94.5 | 94.5 | 94.5
214 |  | Rank (and not reduced to 0 after today)
215 |  | Rank 1 - The MOST important | 1 | [5 empty] | 76 | 76 | 76 | 73 | 69 | 64 | 51.5 | 40.5 | 35.5 | 30.5 | 23.5 | 8.5 | 8 | 2 | 2 | 0
216 |  |  | 2 | [5 empty] | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 11 | 9 | 8 | 3.5 | 0.5 | 0.5 | 0 | 0 | 0
217 |  |  | 3 | [5 empty] | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 6.5 | 5 | 5 | 5 | 4.5 | 2.5 | 0
218 |  |  | 4 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
219 |  | Rank 5 - The LEAST important | 5 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
220
221 |  | Assigned (Replace these with your team members!)
222 |  | Amy Liu | AL |  |  |  |  | AL | 24 | 24 | 24 | 24 | 21 | 21 | 17.5 | 15.5 | 15.5 | 13.5 | 13.5 | 7 | 6.5 | 4 | 1.5 | 0
223 |  | Yelena Pham | YP |  |  |  |  | YP | 26 | 26 | 26 | 26 | 25 | 20 | 15 | 12 | 8 | 8 | 6 | 4 | 3.5 | 2 | 2 | 0
224 |  | Chris Pike | CP |  |  |  |  | CP | 18 | 18 | 18 | 18 | 18 | 18 | 17 | 14 | 13 | 11 | 6.5 | 6 | 5 | 4.5 | 3.5 | 0
225 |  | Shane Schulte | SS |  |  |  |  | SS | 26.5 | 26.5 | 26.5 | 26.5 | 26.5 | 26.5 | 23.5 | 18.5 | 15.5 | 13.5 | 12 | 4.5 | 4.5 | 0 | 0 | 0
226 |  | All | ALL |  |  |  |  | ALL | 21 | 21 | 21 | 18 | 18 | 18 | 18 | 18 | 18 | 18 | 12 | 9 | 9 | 5 | 5 | 0
227 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
228 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
229 | [7 empty] | Unassigned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
230 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
231 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
232 | [8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
233
234
235 | [7 empty] | DateLine | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5 | 93.5
236

## Daily Scrum
Producer | 2016-12-16 |  | Team Members
Approved | Dates |  | Amy Liu | Yelena Pham | Chris Pike | Shane Schulte | All
| 2016-10-26 | Wed | Done: Talked about level design Next: Can't work tomorrow Help: Nothing now | Done: Brainstorming ideas Next: Help: | Done: Brainstorming ideas Next: Help: | Done: Brainstorming ideas Next: Help: | Done: Next: Help:
| 2016-10-27 | Thu | Done: Nothing today Next: Sketch 1st level Help: Need to chat with people about designs for 1st level | Done: Brainstorming ideas Next: Help: | Done: Brainstorming ideas Next: Help: | Done: Brainstorming ideas Next: Help: | Done: Next: Help:
| 2016-10-28 | Fri | Done: Sketched 1st level Next: Whitebox the level Help: — | Done: Brainstorming ideas Next: Help: | Done: Brainstorming ideas Next: Help: | Done: Brainstorming ideas Next: Help: | Done: Next: Help:
| 2016-10-29 | Sat | Done: Next: Help: | Done: Brainstorming ideas Next: Help: | Done: Brainstorming ideas Next: Help: | Done: Brainstorming ideas Next: Help: | Done: Next: Help:
| 2016-10-30 | Sun | Done: Next: Help: | Done: Brainstorming ideas Next: Help: | Done: Brainstorming ideas Next: Help: | Done: Brainstorming ideas Next: Help: | Done: Next: Help:
| 2016-10-31 | Mon | Done: Next: Help: | Done: Brainstorming ideas Next: Help: | Done: Brainstorming ideas Next: Help: | Done: Brainstorming ideas Next: Help: | Done: Next: Help:
| 2016-11-01 | Tue | Done: Brainstorming Next: Engineer movement/camera movement Help: | Done: Decided on game design Next: Help: | Done: Decided on game design Next: Help: | Done: Decided on game design Next: Help: | Done: Next: Help:
| 2016-11-02 | Wed | Done: Engineer movement/camera movement Next: Engineer interactions Help: | Done: Next: Help: | Done: N/A Next: Underwater design Help: | Done: Fleshed out details of game design Next: Work on ship design | Done: Next: Help:
| 2016-11-03 | Thu | Done: Next: Help: | Done: Next: Help: | Done: Next: Underwater or Space design Help: Sick | Done: Nothing Next: Work on ship design | Done: Next: Help:
| 2016-11-04 | Fri | Done: Next: Help: | Done: Next: Help: | Done: Next: Help: Sick | Done: Tried to work on ship design, got stuck Next: Continue Help: Meet up with team and get a ship idea together | Done: Next: Help:
| 2016-11-05 | Sat | Done: Next: Help: | Done: Next: Help: | Done: Next: Help: Sick | Football | Done: Next: Help:
| 2016-11-06 | Sun | Done: Next: Help: | Done: Ship movement Next: Help: Issues with Git access and using a controller on a Mac | Done: Next: Help: Sick | Done: Tried to work again, lots of merge conflicts prevented progress on actual game | Done: Next: Help:
| 2016-11-07 | Mon | Done: multiplayer controller input, bug fixes, merge issues Next: engineer interactions Help: | Done: Started working on firing bullets and split screen four ways Next: Allow ships to attack each other and clean up shooting Help: | Done: Next: Help: Sick | Done: met to talk about design choices after prototype | Done: Next: Help:
| 2016-11-08 | Tue | Done: Next: Help: | Done: Next: Help: | Done: Next: Help: Sick | Done: started working on concept art for spaceship and interior design | Done: Next: Help:
| 2016-11-09 | Wed | Done: hull breaches Next: fixing gravity generator Help: | Done: Game layout Next: Help: | Done: Next: Learning code base Help: Other homework | Done: started modeling spaceship | Done: Next: Help:
| 2016-11-10 | Thu | Done: Added slider bar to hull breaches Next: Fixing gravity generator Help: | Done: Next: Help: | Done: Learning code base Next: Damage distribution Help: Other homework | Done: still modeling ship
| 2016-11-11 | Fri | Done: Button sequence for fixing gravity generator, control module, etc Next: secondary turrets Help: | Done: Next: Help: | Done: NA Next: Research and Analysis Help: | didn't work today
| 2016-11-12 | Sat | Done: Secondary turret Next: testing and bug fixes Help: | Done: Next: Help: | Done: NA Next: Research and Analysis Help: | Done: spaceship complete, UV mapped ship and implemented it into the scene
| 2016-11-13 | Sun | Done: testing and bug fixes Next: Bullet bug Help: | Done: Research and Analysis doc, asteroids getting destroyed, start menu Next: Help: Controller still doesn't work... | Done: Research and Analysis Next: Rewriting Damage distribution Help: | Done: Research and analysis + getting gold spike ready
| 2016-11-14 | Mon | Done: Bullet fixes Next: playtest feedback tweaks Help: | Done: Got controllers! Next: Help: | Done: NA Next: Refactoring /Repo Cleanup Help: | Done: bugfixing
| 2016-11-15 | Tue | Done: Camera clipping fix and engineer movement fix Next: Engineer testing and tweaks Help: | Done: Began working on wormhole track Next: Help: | Done: Refactoring /Repo Cleanup Next: Help: | Done: playtesting and tweaks
| 2016-11-16 | Wed | Done:Engineer tweaks Next: Add ship interior to main scene Help: | Done: Created wormhole, some issues with physics Next: Help: | Done: NA Next: NA Help: | 485 project
| 2016-11-17 | Thu | Done: Added ship interior Next: Refactor turret classes Help: | Done: Made wormhole texture and ships can fly through Next: Help: | Done: NA Next: DamgeController, InControl Help: | Tweaked controls of the engineer
| 2016-11-18 | Fri | Done: Refactor turret classes Next: Add ship components Help: | Done: Worked on ship controls Next: Help: Controls are a little finicky | Done: NA Next: DamgeController, InControl Help:
| 2016-11-19 | Sat | Done: Next: gamejam Help: | Done: Next: Help: | Done: Damage Controler Rewrite Next: InControl Help: | Done: nothing
| 2016-11-20 | Sun | Done: Next: Help: | Done: Next: Help: | Done: Next: InControl Help: | Done: nothing
| 2016-11-21 | Mon | Done: Added ship components to interior Next: Finish ship components breaking Help: | Done: Dumped the wormhole and we're using rings instead Next: Help: | Done: Inserting InControl, Next: Help: | Refactored repair system
| 2016-11-22 | Tue | Done: Finished ship components breaking negative effects Next: Added components, test and debug Help: | Done: Next: Help: | Done: Start Screen, ReadyCheck Screen, RaceScene Next: Help: | Done:
| 2016-11-23 | Wed | Done: Added components Next: test and debug components Help: | Done: Next: Help: | Done: Command Center Next: Help: | Done: added shields and boosts using power bar
| 2016-11-24 | Thu | Done: Next: Help: | Done: ate some turkey Next: Help: | Done: Turkey Next: Help: | Thanks
| 2016-11-25 | Fri | Done: bug fixes for components Next: Command center and engine Help: | Done: Next: Help: | Done: Sleeping Next: Help: | Giving
| 2016-11-26 | Sat | Done: Command center and engine Next: Redo ready check screen, gameover scenes Help: | Done: Updated game track Next: Help: | Done: Boardgames Next: Help: | Break
| 2016-11-27 | Sun | Done: Redid ready check screen to allow picking roles, gameover scenes Next: Pilot hud, powerup bar Help: | Done: Fixed asteroid behavior, started working on ship indicators Next: Help: | Done: Sounds, Vibrations, Next: Help: | Done: Textured interior of ship, bugfixing
| 2016-11-28 | Mon | Done: Pilot hud, powerup bar Next: Add queue for pilot hud Help: | Done: Cleaned up some code, working on "tutorial" Next: Get control working on start screen Help: | Done: Class Stuff Next: Help: | Done: Next: Help:
| 2016-11-29 | Tue | Done: pilot warnings Next: clamp turret Help: | Done: Next: Help: | Done: Next: Xhair, vibrations, wrench model Help: | Done: Next: Help:
| 2016-11-30 | Wed | Done: clamp turret Next: redo turret hull breach ui Help: | Done: Next: Help: | Done: Xhair, vibrations, wrench model Next: Wrench and Engine Help: | TODO: revise asteroid movement/spawning, revisit damage and shields, add race progress meter, clamp the turrets
| 2016-12-01 | Thu | Done: redo turret hull breach ui Next: Help: | Done: Playtested train track trouble and our game Next: Help: | Done: Next: Wrench and Engine Help: | Done: Rebalanced damage and shields, added race meter Next: Help:
| 2016-12-02 | Fri | Done: Next: Help: | Done: Next: Help: | Done: Wrench and Engine Next: Help: | Done: Updated asteroid models + general movement and spawning with the map Next: Help:
| 2016-12-03 | Sat | Done: redo turret hull breach ui Next: explosions for bullets Help: | Done: Next: Help: | Done: Next: Help: | Done: Playtested other game + got feedback on our game, minor revisions and tweaks Next: Keep polishing the game Help:
| 2016-12-04 | Sun | Done: explosions for bullets Next: start screen/gameover screen makeover Help: | Done: Enter turret button indicator, more obvious boost when ship goes through ring Next: Help: | Done: Next: Help: | Done: Updated ready check scene to be more intuitive Next: Continue polish, bugfixing and playtesting Help:
| 2016-12-05 | Mon | Done:start screen/gameover screen makeover Next: engine start bug Help: | Done: Update tutorial Next: Leave turret button indicator, engineer wrench movement, polish Help: | Done: Playtesting Next: Wrench and Engine Help: | Done: Playtesting Next: Continue playtesting / balancing values Help:
| 2016-12-06 | Tue | Done: engine start bug Next: add countdown before game and cutscene Help: | Done: Next: Help: | Done: Next: Wrench and Engine Tweaks Help: | Nothing
| 2016-12-07 | Wed | Done: Animate gameover cutscene and countdown Next: Add fade in Help: | Done: Next: Help: | Done: Wrench and Engine Tweaks Next: Help: | Reworked power, need help figuring out if it's more effective now
| 2016-12-08 | Thu | Done: Added fade in and various bug fixes Next: Add delay to gameover Help: | Done: Added delay to tutorial Next: Help: | Done: Next: Help: | 485 project :(
| 2016-12-09 | Fri | Done: Added delay to gameover scene Next: Add countdown for respawn Help: | Done: Worked on respawn, added music to menus and tutorials Next: Help: Get to respawn to correct ring | Done: Next: Help: | Reverted power back to old system with adjustments
| 2016-12-10 | Sat | Done: Next: Help: | Done: Worked on trailer Next: Help: | Done: Next: Help: | Nothing
| 2016-12-11 | Sun | Done: Next: Help: | Done: Worked on trailer Next: Help: | Done: Next: Help: | Balance tweaks
| 2016-12-12 | Mon | Done: Added countdown for respawn, bug fixes Next: wrench animations Help: | Done: Worked on trailer Next: Help: | Done: Next: Birthday Fun Help: | Done: Added trail renderers to ship, bugfixes with rings and dmg
| 2016-12-13 | Tue | Done: up and down wrench animations Next: bugs Help: | Done: Next: Help: | Done: Next: Help: | Done: reworked rings to disappear as you fly through them
| 2016-12-14 | Wed | Done: Next: Help: | Done: Next: Help: | Done: Next: Help: | Nothing
| 2016-12-15 | Thu | Done: Next: Help: | Done: Next: Help: | Done: Next: Justification and Peer Review Help: | Nothing
| 2016-12-16 | Fri | Done: finished wrench animations, wrench sound effect, bug fixes, reset game in game function, Next: Help: | Done: Add music to end scene, delay tutorial buttons, update trailer Next: SHOWCASE Help: | Done: Justification, Peer Review, Showcase! Next: Play VGs and BGs on break Help: | Done: Showcase!